## Sheet1
User Story | To Do | In Progress | Done
As a user, I want to see all my incomes and expenses in time order. |  |  | Create a bar that can show the detail of a single income/expense (5 hrs)
Display few bars on the main page (2 hrs)
Make the income/expense bar time-ordered (2 hrs)
Test & Improvement (2 hrs)
As a user, I want to see the summary of my income and expense in a visual diagram. |  |  | Create a visual diagram to show the data (5 hrs)
Show the summary diagram on the second page (3 hrs)
Test & Improvement (5 hrs)
As a user, I need a user login page |  |  | Create the user login page that can perform login functions (4 hrs)
Record user’s data (2 hrs)
Perform login function on different devices (10 hrs)
Test & Improvement (9 hrs)