## Sheet1
User Story | To Do | In Progress | Done
As a user, I want to have a Main Menu page that contains all of my records organized and functional buttons so that I can track my payments by viewing the record term by term. |  | Implement the history functional button in Main Menu on AS. Connect the main history bill pages (3 hrs)(Luke, Yujia) | Implement the add bill functional button in Main page on AS. Connect the add bill page (3 hrs)(Luke, Yujia)
Implement the navigation bar in Main page on AS. Connect corresponding pages. Needn’t build the corresponding pages (2 hrs)(Qingyuan)
Test & Improvement (2 hrs)(Yujia)
As a user, I want to add/delete/edit/view my record in my account page so that I can track my payments. |  | Implement the basic UI pages on AS (10 hrs)(Joseph, Luke, Qingyuan, Yujia, Xuhua)
Implement the data interaction function between user page with database to save/change/delete data (10 hrs)(Joseph, Yujia, Luke)
Test & Improvement (10 hrs)
As a user, I want to jump among pages so that I can operate this application. |  | Jump from the main page to other pages (3 hrs)(Luke, Qingyuan)
Jump from the add bill page to other pages (1 hrs)(Joseph, Yujia)
Jump from the calendar page to other pages (3 hrs)(Xuhua)
Jump from the analysis page to other pages (3 hrs)(Qingyuan)
As a developer, I write and read users’ input data into database, so that I can operate data in different functions. |  |  | Get the input from users (3 hrs)(Yujia, Joseph)
Write the input into database (6 hrs)(Joseph, Yujia)
Read the data from database (3 hrs)(Luke, Yujia)
Get connection with firebase (1 hrs)(Joseph, Luke, Qingyuan, Yujia, Xuhua)
3 | 53 | 2018-07-10
6 | 53 | 2018-07-11
8 | 53 | 2018-07-12
8 | 53 | 2018-07-13
8 | 53 | 2018-07-14
11 | 53 | 2018-07-15
20 | 63 | 2018-07-16