## Sheet1
User Story | To Do | In Progress | Finished
As a user, I want to have a Main Menu page that contain all of my records in an organized way and functional buttons so that I can track my payments by viewing the record term by term. |  |  | Navigation bar(1 hrs)(Qingyuan)
|  | Main page(Luke) | Links between button(2 hrs)(Yujia)
Implement the functional buttons in Main Menu on AS. It doesn’t need to connect to the related function but just UI (6 hrs)
Design the Main Menu (2 hrs) (Hang)
Implement the UI for Main Menu on Android Studio(AS in short) (5 hrs) (Yujia, Qingyuan)
Test & Improvement (2 hrs)
As a user, I want to add/delete/edit/view my record in my account page so that I can track my payments |  | Design the pages:Calendar Page (1 hr) (Xuhua) | Implement the basic UI pages on AS (5 hrs each page)(Hang, Yujia)
Design the pages:Analysis Page (1 hr)(Qingyuang)
Design the pages:Basic Add New Record Page (1 hr)(Hang)
Implement the data interaction function between user page with database to save/change/delete data (7 hrs each page)
Test & Improvement (1 hr each page)
0 | 34 | 2018-07-03
0 | 34 | 2018-07-04
0 | 34 | 2018-07-05
3 | 34 | 2018-07-06
8 | 34 | 2018-07-07
16 | 34 | 2018-07-08
21 | 34 | 2018-07-09